## Calendar Plan
Calendar Plan of Key Data Migration Management Activities for the New Implementation of SAP S/4HANA 2020 at XXXXX
|  |  | Workstream Lead | Aleksei Arziaev |  | *Type of Migration Activity:
|  |  | Project Plan | Hyperlink Project Plan |  | DOC | - Document
|  |  | Data Migration Status | Hyperlink Data Migration Status |  | JFM | - Jour fixe, Kick-off and other Meetings
|  |  | Data Object Migration Cards | Hyperlink Folder Data Object Migration Cards |  | PRC | - Process (test, data migration, etc.) | [6 empty] | Go to the Current Day:
|  |  | Data Migration Test Plans | Hyperlink Data Migration Test Plans |  | WSH | - Workshop | [6 empty] | #N/A | January 23 | [6 empty] | January 23 | [6 empty] | January 23 | [6 empty] | January 23 | [6 empty] | February 23 | [6 empty] | February 23 | [6 empty] | February 23 | [6 empty] | February 23 | [6 empty] | March 23 | [6 empty] | March 23 | [6 empty] | March 23 | [6 empty] | March 23 | [6 empty] | March 23 | [6 empty] | April 23 | [6 empty] | April 23 | [6 empty] | April 23 | [6 empty] | April 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | June 23 | [6 empty] | June 23 | [6 empty] | June 23 | [6 empty] | June 23 | [6 empty] | July 23 | [6 empty] | July 23 | [6 empty] | July 23 | [6 empty] | July 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | September 23 | [6 empty] | September 23 | [6 empty] | September 23 | [6 empty] | September 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | December 23 | [6 empty] | December 23 | [6 empty] | December 23 | [6 empty] | December 23 | [6 empty] | January 24 | [6 empty] | January 24 | [6 empty] | January 24 | [6 empty] | January 24
|  |  | Data Migration Plan | Hyperlink Data Migration Plan |  | TEC | - Technical Aspects | [6 empty] | Start of the Calendar: | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4
|  |  | Data Acceptance | Hyperlink Folder Data Acceptance |  | OTH | - Others | [6 empty] | 2023-01-01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Type of Mig. Activity* | Critical Activity | Line | Data Migration Activitiy | Responsible (Implementation Partner) | Responsible (Client) | Circle of Participants | Start [DD/MM/YYYY] | Start Time [GMT+02.00] | Finish [DD/MM/YYYY] | Finish Time [GMT+02.00] | Status [0 bis 100] | Milestone [DD/MM/YYYY] | Finished [f] | Commentary | time axis 2023-01-01 to 2024-01-27
|  | X | 2. Data Migration Planning and Preparation Phase |  |  |  | 2023-01-02 |  | 2023-02-28
JFM |  |  | Defining the organizational structure of the data migration workstream and assigning responsibilities | Data Migration Workstream Lead | Client Representative for Data Migration |  | 2024-01-02 |  | 2023-01-05 |  | 98% | 2023-01-05 | f
JFM |  |  | Conducting a Kick-off meeting with the data migration workstream (implementation partner only) and setting goals for the second data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-01-09 | 9:00 | 2023-01-09 | 10:00 | 100% | 2023-01-09 | f
JFM |  |  | Conducting a Kick-off meeting with the whole data migration workstream | Data Migration Workstream Lead | Client Representative for Data Migration | Data Migration Workstream and Stakeholders | 2023-01-11 | 10:00 | 2023-01-11 | 11:00 | 100% | 2023-01-11 | f | bar: 2023-01-04
DOC | X |  | Developing of the Data Migration Concept | Data Migration Workstream Lead |  |  | 2023-01-02 |  | 2023-01-13 |  | 98% | 2023-01-13 | f
OTH |  |  | Aligning the Data Migration Concept with the Client and its signing | Data Migration Workstream Lead | Client Representative for Data Migration |  | 2023-01-16 | 9:00 | 2023-01-16 | 12:00 | 100% | 2023-01-16 | f
WSH |  |  | Сommunicating the Data Migration Concept to the entire data migration workstream | Data Migration Workstream Lead |  |  | 2023-01-17 | 10:30 | 2023-01-17 | 264:00 | 100% | 2023-01-17 | f
OTH |  |  | Clarifying the budget for the data migration process | Data Migration Workstream Lead |  |  | 2023-01-18 |  | 2023-01-18 |  | 100% | 2023-01-18 | f
OTH |  |  | Сommunicating the Data Migration Concept to the project management | Data Migration Workstream Lead |  |  | 2023-01-19 | 13:00 | 2023-01-19 | 14:00 | 100% | 2023-01-19 | f
JFM |  |  | Jour fixe for the preparation and planning phase | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-01-02 |  | 2023-02-28 |  | 100% | 2023-02-28 | f | Every Tuesday and Thursday
DOC | X |  | Developing of the Calendar Plan of Key Data Migration Management Activitites | Data Migration Workstream Lead |  |  | 2023-01-05 |  | 2023-01-20 |  | 100% | 2023-01-20 | f
WSH |  |  | Holding a workshop to the Data Object Migration Card and the Data Migration Status | Data Migration Workstream Lead | Client Representative for Data Migration | Data Migration Workstream | 2023-01-10 | 9:00 | 2023-01-10 | 12:00 | 100% | 2023-01-10 | f
TEC |  |  | Defining cleansing measures for migration objects and their documenting in the Data Object Migration Cards | Functional and Migration Consultants (Migration Workstream) |  |  | 2023-01-16 |  | 2023-01-31 |  | 100% | 2023-01-31 | f
TEC | X |  | Preparing the data migration system (MIG/1) for the first (functional) data migration test | Technical architecture and infrastructure workstream |  |  | 2023-02-13 |  | 2023-02-17 |  | 100% | 2023-02-17 | f
TEC |  |  | Checking the system (customizing settings) after its creation | Functional Consultants (Migration Workstream) |  |  | 2023-02-20 |  | 2023-02-21 |  | 100% | 2023-02-21 | f
TEC |  |  | Copying of the legacy system (ECC) before data cleansing (separate client) | Technical architecture and infrastructure workstream |  |  | 2023-02-28 |  | 2023-02-28 |  | 100% | 2023-02-28 | f
TEC | X |  | Copying of the legacy system (ECC) for design of data migration | Technical architecture and infrastructure workstream |  |  | 2023-02-28 |  | 2023-02-28 |  | 100% | 2023-02-28 | f
JFM |  |  | Summing up the results of the second data migration phase | Data Migration Workstream Lead | Client Representative for Data Migration | Data Migration Workstream and Stakeholders | 2023-02-28 | 11:00 | 2023-02-28 | 12:00 | 100% | 2023-02-28 | f
|  | x | 3. Data Migration Design Phase |  |  |  | 2023-03-01 |  | 2023-07-16
JFM |  |  | Setting goals for the third data migration phase | Data Migration Workstream Lead | Client Representative for Data Migration | Data Migration Workstream and Stakeholders | 2023-03-01 | 9:00 | 2023-03-01 | 10:00 | 100% | 2023-03-01 | f
DOC | X |  | Developing the 1. Data Migration Test Plan | Data Migration Workstream Lead |  |  | 2023-03-01 |  | 2023-03-10 |  | 100% | 2023-03-10 | f
TEC | X |  | Developing of data migration projects and programs | Data Migration Workstream |  |  | 2023-03-01 |  | 2023-04-21 |  | 100% | 2023-04-21 | f
DOC |  |  | Preparing value mappings | Data Migration Workstream | Client Representatives |  | 2023-03-01 |  | 2023-03-31 |  | 100% | 2023-03-31 | f
DOC | X |  | Finalising Data Object Migration Cards | Data Migration Workstream |  |  | 2023-03-01 |  | 2023-03-31 |  | 100% | 2023-03-31 | f
DOC | X |  | Developing Data Migration Runbooks | Data Migration Workstream |  |  | 2023-03-01 |  | 2023-04-15 |  | 100% | 2023-04-15 | f
PRC |  |  | Conducting data cleansing | Data Migration Workstream | Client Representatives |  | 2023-03-01 |  | 2023-04-30 |  | 100% | 2023-04-30 | f
TEC | X |  | Copying of the legacy system (ECC) for the first data migration test | Technical architecture and infrastructure workstream |  |  | 2023-03-31 |  | 2023-03-31 |  | 100% | 2023-03-31 | f
PRC | X |  | 1. Data Migration (Functional) Test | Data Migration Workstream |  |  | 2023-04-03 | 9:00 | 2023-04-30 | 12:00 | 100% | 2023-04-30 | f
PRC |  |  | Verifying data after migration | Data Migration Workstream | Reviewers |  | 2023-04-15 |  | 2023-05-05 | 15:00 | 100% | 2023-05-05 | f
JFM |  |  | Jour fixe for the design phase | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-03-01 | 10:00 | 2023-07-16 | 10:30 | 100% | 2023-07-16 | f | Every Tuesday and Thursday
OTH |  |  | Fine-tuning data migration sequence | Data Migration Workstream Lead |  |  | 2023-04-01 |  | 2023-06-30 |  | 100% | 2023-06-30 | f | During data migration tests
DOC |  |  | Finalising value mappings | Data Migration Workstream | Client Representatives |  | 2023-05-02 |  | 2023-05-31 |  | 100% | 2023-05-31 | f
DOC | X |  | Developing the 2. Data Migration Test Plan | Data Migration Workstream Lead |  |  | 2023-05-08 |  | 2023-05-15 |  | 100% | 2023-05-15 | f
TEC | X |  | Preparing the data migration system (MIG/2) for the second data migration test | Technical architecture and infrastructure workstream |  |  | 2023-05-08 |  | 2023-05-15 |  | 100% | 2023-05-15 | f
TEC |  |  | Checking the system (customizing settings) after its creation | Functional Consultants (Migration Workstream) |  |  | 2023-05-16 |  | 2023-05-17 |  | 100% | 2023-05-17 | f
JFM |  |  | Summing up the results of the first data migration (functional) test and setting goals for the period until the next data migration test | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-05-03 | 14:00 | 2023-05-03 | 15:00 | 100% | 2023-05-03 | f
TEC |  |  | Adjusting migration programs and projects after the functional test | Data Migration Workstream |  |  | 2023-05-08 |  | 2023-05-31 |  | 100% | 2023-05-31 | f
TEC | X |  | Copying of the legacy system (ECC) for the second data migration test | Technical architecture and infrastructure workstream |  |  | 2023-05-31 |  | 2023-05-31 |  | 100% | 2023-05-31 | f
TEC | X |  | Importing data migration programs, projects and value mappings into the MIG/2 | Data Migration Workstream |  |  | 2023-06-01 |  | 2023-06-01 |  | 100% | 2023-06-01 | f
PRC | X |  | 2. Data Migration Test | Data Migration Workstream |  |  | 2023-06-05 | 9:00 | 2023-06-30 | 12:00 | 100% | 2023-06-30 | f
PRC | X |  | Performance Test | Data Migration Workstream, Technical architecture and infrastructure workstream |  |  | 2023-06-05 |  | 2023-06-30 | 12:00 | 100% | 2023-06-30 | f
TEC | X |  | Copying of the legacy system (ECC) for the third data migration test | Technical architecture and infrastructure workstream |  |  | 2023-06-30 |  | 2023-06-30 |  | 100% | 2023-06-30 | f
PRC | X |  | Verifying data after migration | Data Migration Workstream | Reviewers |  | 2023-06-08 |  | 2023-07-05 | 15:00 | 100% | 2023-07-05 | f
TEC |  |  | Adjusting migration programs and projects after the second data migration test | Data Migration Workstream |  |  | 2023-06-30 |  | 2023-07-13 |  | 100% | 2023-07-13 | f
DOC | X |  | Developing the 3. Data Migration Test Plan | Data Migration Workstream Lead |  |  | 2023-07-03 |  | 2023-07-07 |  | 100% | 2023-07-07 | f
JFM |  |  | Summing up the results of the second data migration test | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-07-06 | 9:30 | 2023-07-06 | 10:00 | 100% | 2023-07-06 | f
TEC | X |  | Preparing the quality assurance system (QAS/1) for the third data migration test | Technical architecture and infrastructure workstream |  |  | 2023-07-03 |  | 2023-07-11 |  | 100% | 2023-07-11 | f
TEC |  |  | Checking the system (customizing settings) after its creation | Functional Consultants (Migration Workstream) |  |  | 2023-07-12 |  | 2023-07-13 |  | 100% | 2023-07-13 | f
TEC | X |  | Importing data migration programs, projects and value mappings into the QAS/1 | Technical architecture and infrastructure workstream |  |  | 14/072023 |  | 14/072023 |  | 100% | 14/072023 | f
JFM |  |  | Summing up the results of the second data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 14/072023 | 13:00 | 14/072023 | 14:00 | 100% | 14/072023 | f
|  | x | 4. Data Migration Validation Phase |  |  |  | 2023-07-17 |  | 2023-11-30
JFM |  |  | Setting goals for the fourth data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 2023-07-17 | 9:00 | 2023-07-17 | 10:00 | 100% | 2023-07-17 | f
JFM |  |  | Jour fixe for the validation phase | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-07-17 | 10:00 | 2023-11-30 | 10:30 | 100% | 2023-11-30 | f | Every Tuesday and Thursday
PRC | X |  | 3. Data Migration Test | Data Migration Workstream |  |  | 2023-07-17 | 10:00 | 2023-08-04 | 12:00 | 100% | 2023-08-04 | f
DOC |  |  | Refining value mappings | Data Migration Workstream | Client Representatives |  | 2023-07-17 |  | 2023-11-29 |  | 100% | 2023-10-22 | f
PRC | X |  | Verifying data after the 3. data migration test | Data Migration Workstream | Reviewers |  | 2023-07-19 |  | 2023-08-04 | 15:00 | 100% | 2023-08-04 | f
TEC | X |  | Preparing the quality assurance system (QAS/2) for the fourth data migration test | Technical architecture and infrastructure workstream |  |  | 2023-08-09 |  | 2023-08-16 |  | 100% | 2023-08-16 | f
TEC |  |  | Checking the system (customizing settings) after its creation | Functional Consultants (Migration Workstream) |  |  | 2023-08-17 |  | 2023-08-18 |  | 100% | 2023-08-18 | f
DOC | X |  | Developing the 4. Data Migration Test Plan | Data Migration Workstream Lead |  |  | 2023-08-14 |  | 2023-08-18 |  | 100% | 2023-08-18 | f
JFM |  |  | Summing up the results of the third data migration test | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-08-08 | 9:30 | 2023-08-08 | 10:00 | 100% | 2023-08-08 | f
TEC |  |  | Adjusting migration programs and projects after the third data migration test | Data Migration Workstream |  |  | 2023-08-05 |  | 2023-08-30 |  | 100% | 2023-08-30 | f
TEC | X |  | Copying of the legacy system (ECC) for the fourth data migration test | Technical architecture and infrastructure workstream |  |  | 2023-08-31 |  | 2023-08-31 |  | 100% | 2023-08-31 | f
TEC | X |  | Importing data migration programs, projects and value mappings into the QAS/2 | Data Migration Workstream |  |  | 2023-09-01 |  | 2023-09-01 |  | 100% | 2023-09-01 | f
PRC | X |  | 4. Data Migration Test | Data Migration Workstream |  |  | 2023-09-04 | 9:00 | 2023-09-22 | 12:00 | 100% | 2023-09-22 | f
PRC | X |  | Verifying data after the 4. data migration test | Data Migration Workstream | Reviewers |  | 2023-09-06 |  | 2023-09-22 | 15:00 | 100% | 2023-09-22 | f
TEC | X |  | Preparing the quality assurance system (QAS/3) for the fifth data migration (cutover) test | Data Migration Workstream |  |  | 2023-10-04 |  | 2023-10-11 |  | 100% | 2023-10-11 | f
TEC |  |  | Checking the system (customizing settings) after its creation | Functional Consultants (Migration Workstream) |  |  | 2023-10-12 |  | 2023-10-13 |  | 100% | 2023-10-13 | f
DOC |  |  | Developing the 5. Data Migration Test Plan (part of a Cutover plan) and including it into the Cutover testing | Data Migration Workstream Lead |  |  | 2023-10-04 |  | 2023-10-13 |  | 100% | 2023-10-13 | f
JFM |  |  | Summing up the results of the fourth data migration test | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-10-26 | 9:30 | 2023-10-26 | 10:00 | 100% | 2023-10-26 | f
TEC |  |  | Adjusting migration programs and projects after the fourth data migration test | Data Migration Workstream |  |  | 2023-09-25 |  | 2023-10-13 |  | 100% | 2023-10-13 | f
TEC | X |  | Copying of the legacy system (ECC) for the fifth data migration test | Technical architecture and infrastructure workstream |  |  | 2023-09-30 |  | 2023-09-30 |  | 100% | 2023-09-30 | f
TEC | X |  | Importing data migration programs, projects and value mappings into the QAS/3 | Data Migration Workstream |  |  | 2023-10-20 |  | 2023-10-20 |  | 100% | 2023-10-20 | f
PRC | X |  | 5. Data Migration Test | Data Migration Workstream |  |  | 2023-10-23 | 9:00 | 2023-11-10 | 12:00 | 100% | 2023-11-10 | f
PRC | X |  | Verifying data after the 5. data migration test | Data Migration Workstream | Reviewers |  | 2023-10-25 |  | 2023-11-10 | 15:00 | 100% | 2023-11-10 | f
TEC | X |  | Preparing the new productive system for the productive upload | Technical architecture and infrastructure workstream |  |  | 2023-11-01 |  | 2023-11-10 |  | 100% | 2023-11-10 | f
TEC |  |  | Checking the system (customizing settings) after its creation | Functional Consultants (Migration Workstream) |  |  | 2023-11-13 |  | 2023-11-15 |  | 100% | 2023-11-15 | f
DOC | X |  | Developing the Data Migration Plan and aligning it with the Client and PMO | Data Migration Workstream Lead | Client Representative for Data Migration | Project Management Office | 2023-11-06 |  | 2023-11-17 |  | 100% | 2023-11-17 | f
DOC |  |  | Including the Data Migration Plan into the Cutover Plan | Data Migration Workstream Lead |  | Cutover Manager | 2023-11-20 |  | 2023-11-24 |  | 100% | 2023-11-24 | f
DOC | X |  | Developing data acceptance procedure and data acceptance form | Data Migration Workstream Lead | Client Representative for Data Migration |  | 2023-10-09 |  | 2023-10-13 |  | 100% | 2023-10-13 | f
OTH |  |  | Aligning the data acceptance procedure with the auditor |  | Client Representative for Data Migration |  | 2023-10-15 |  | 2023-10-17 |  | 100% | 2023-10-17 | f
WSH |  |  | Conducting a workshop to data acceptance | Data Migration Workstream Lead |  |  | 2023-10-19 | 9:00 | 2023-10-19 | 12:00 | 100% | 2023-10-19 | f
JFM |  |  | Summing up the results of the fifth data migration test | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-11-27 | 15:00 | 2023-11-27 | 16:00 | 100% | 2023-11-27 | f
TEC | X |  | Importing data migration programs, projects and value mappings into the productive system | Data Migration Workstream |  |  | 2023-11-30 |  | 2023-11-30 |  | 100% | 2023-11-30 | f
JFM |  |  | Summing up the results of the fourth data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 2023-11-30 | 13:00 | 2023-11-30 | 14:00 | 100% | 2023-11-30 | f
|  | x | 5. Data Migration Phase |  |  |  | 2023-12-01 |  | 2024-01-11
JFM |  |  | Setting goals for the actual data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 2023-12-01 | 8:00 | 2023-12-01 | 8:30 | 100% | 2023-12-01 | f
JFM |  |  | Jour fixe for the data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream | 2023-12-04 | 17:00 | 2024-01-07 | 17:15 | 100% | 2024-01-07 | f | Every Day
PRC | X |  | Actual Data Migration | Data Migration Workstream |  |  | 2023-12-01 | 8:00 | 2024-01-10 | 17:00 | 100% | 2024-01-07 | f | According to the Data Migration / Cutover Plan
OTH | X |  | Posting free period (stopping operating processes) | Client |  |  | 2024-01-05 | 18:00 | 2024-01-11 | 8:00 | 100% | 2024-01-05 | f
OTH | X |  | Point of No Return |  |  |  | 2024-01-09 | 8:00 | 2024-01-09 | 8:00 | 100% | 2024-01-09 | f
PRC | X |  | Data Acceptance | Data Migration Workstream | Reviewers |  | 2023-12-01 | 8:00 | 2024-01-10 | 17:00 | 100% | 2024-01-10 | f | According to the Data Migration / Cutover Plan
OTH | X |  | Go-Live |  |  |  | 2024-01-11 | 8:00 | 2024-01-11 | 8:00 | 100% | 2024-01-11 | f
JFM |  |  | Summing up the results of the actual data migration | Data Migration Workstream Lead |  | Data Migration Workstream | 2024-01-11 | 9:00 | 2024-01-11 | 9:30 | 100% | 2024-01-08 | f
JFM |  |  | Summing up the results of the data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 2024-01-11 | 16:00 | 2024-01-11 | 17:00 | 100% | 2024-01-08 | f
|  | x | 6. Post-Data Migration Phase |  |  |  | 2024-01-12 |  | 2024-01-19
JFM |  |  | Setting goals for the last data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 2024-01-12 | 9:30 | 2024-01-08 | 10:00 | 100% | 2024-01-08 | f
JFM |  |  | Jour fixe for the last data migration phase | Data Migration Workstream Lead |  | Data Migration Workstream | 2024-01-12 | 10:00 | 2024-01-19 | 10:30 | 100% | 2024-01-19 | f | Every Tuesday and Thursday
PRC |  |  | Migrating historical data | Data Migration Workstream |  |  | 2024-01-12 | 10:00 | 2024-01-12 | 14:00 | 100% | 2024-01-10 | f
PRC |  |  | Accepting historical data | Data Migration Workstream | Reviewers |  | 2024-01-12 | 14:00 | 2024-01-12 | 17:00 | 100% | 2024-01-11 | f
DOC | X |  | Finalizing the data migration documentation and saving it on the MT platform | Data Migration Workstream | Client Representative for Data Migration |  | 2024-01-12 |  | 2024-01-18 |  | 100% | 2024-01-18 | f
JFM |  |  | Summing up the results of the whole migration process | Data Migration Workstream Lead |  | Data Migration Workstream and Stakeholders | 2024-01-19 | 10:00 | 2024-01-19 | 12:00 | 100% | 2024-01-19 | f
Note on O5: Tap "Today" to go to the current day on the calendar
Note on O7: Set the start date for the data migration process

## Definition of Color
Definition of Color
1. Time Bar
2. Day Bar
3. Milestone
A= | 1 | B= | 1 | C= | 2 | D= | 2
Green bright
Blue bright
Red bright
Blue gray bright
Green
Blue gray
Red
Blue gray dark
Choose the color:
A = Plan
B = Finished
Yellow
Orange
Blue
Gray
Blue dark
Red dark
Green dark
Gray dark
D = Milestone
C = Day Bar
Choose the color:
Choose the colou: