## Data Migration Status
N | SAP Module | Migration Object | Object Type | Object Migration Status | Quantity | The Need of Data Cleansing | Complexity | Object Dependencies | Migration Sequence | Data Object Migration Card (Hyperlink) | Functional Consultant | Migration Consultant | Developer | Extraction Path | Transformation Path | Load Path | Migration Approach | Time Required for Creation of Migration Program/ Project (PD) | Reviewer from Client | Double Maintenance Required | Migration Project/Program Name | Time Required for PREPARATION of Data Load (hours) | Time Required for DATA LOAD (working hours) | Commentary
SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | SCOPE | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | PLAN | DESIGN | DESIGN | DESIGN | DESIGN & VALIDATION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
1 | FI | Business Partner | Master Data | 10_OK in MIG/2 | 35000 | Yes | Very high | GL Accounts | 2 | 1_Business Partner | J. Smith | S. Dovalin | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data | 25 | T. Moorelock | Yes | FI - Business Partner | 4 | 24
2 | FI | GL Accounts | Master Data | 12_Upload Ready to QAS/1 | 1350 | Yes | Medium |  | 1 | 2_GL_Acc | A. Green | S. Dovalin |  | XML (manual file creation) | Standard (Migrate Your Data) or Manually | Standard (Migrate Your Data) | Manually & Migrate Your Data | 12 | J. Barela | Yes | Chart of Accounts | 1 | 2
3 | FI | Assets Master Data | Master Data | 11_Fixing in MIG/2 | 30000 | Yes | Very high | GL Accounts, Internal Orders, Cost Centers, Business Partners | 3 | 3_Assets | K. Clark | S. Tigner | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data | 25 | A. Lolmaugh | No | FI - Assets | 2 | 24
4 | FI | Assets Transactional Data | Transactional Data | 11_Fixing in MIG/2 | 52000 | No | Very high | Assets | 3 | 3_Assets | K. Clark | S. Tigner | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data |  | A. Lolmaugh | No | FI - Assets | 2 | -
5 | FI | SEPA Mandate | Master Data | 12_Upload Ready to QAS/1 | 1250 | Yes | Medium | Business Partners with Customer Role | 3 | 5 SEPA | A. Green | S. Dovalin |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 11 | J. Barela | Yes | FI - SEPA | 1 | 4
6 | CO | Statistical Internal Orders | Master Data | 12_Upload Ready to QAS/1 | 11500 | No | Medium | FI-Characteristics, Cost Centers | 1 | 5_Int ORD | M.A. Wood | S. Dovalin |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 12 | G. Parisot | Yes | CO - Internal Orders | 2 | 4
7 | CO | Cost centers | Master Data | 12_Upload Ready to QAS/1 | 1200 | No | Low | Profit Centers, Segments | 1 | 7 Cost Centers | M.A. Wood | M.A. Wood |  | N/A | Initial Creation | Export/Import | Standard Transaction | 5 | G. Parisot | Yes | n/a | n/a | n/a
8 | CO | Cost Center Std. Hierarchie | Master Data | 12_Upload Ready to QAS/1 | 1 | No | Low | Segments, Profit Center Standard Hierarchy | 1 | 7 Cost Centers | M.A. Wood | M.A. Wood |  | N/A | Initial Creation | Export/Import | Standard Transaction | 1 | G. Parisot | No | n/a | n/a | n/a
9 | FI | Profit center | Master Data | 12_Upload Ready to QAS/1 | 55 | No | Low | Segments | 1 | 9 Profit Center | A. Green | A. Green |  | N/A | Initial Creation | Export/Import | Standard Transaction | 2 | G. Parisot | Yes | n/a | n/a | n/a
10 | FI | Profit Center Std. Hierarchie | Master Data | 12_Upload Ready to QAS/1 | 1 | No | Low |  | 1 | 9 Profit Center | A. Green | A. Green |  | N/A | Initial Creation | Export/Import | Standard Transaction | 1 | G. Parisot | No | n/a | n/a | n/a
11 | FI | Segments | Master Data | 12_Upload Ready to QAS/1 | 5 | No | Low |  | 1 | 11 SEGMENT | A. Green | A. Green |  | N/A | Initial Creation | Export/Import | Standard Transaction | 1 | G. Parisot | Yes | n/a | n/a | n/a
12 | PS | Projects | Master Data | 12_Upload Ready to QAS/1 | 45 | No | Medium | FI-Characteristics, Cost Centers | 2 | 12_Projects | M.A. Wood | M.A. Wood |  | N/A | Initial Creation | Export/Import | Standard Transaction | 15 | G. Parisot | Yes | n/a | 1 | 2
13 | CO | Activity types | Master Data | 12_Upload Ready to QAS/1 | 15 | No | Low | Secondary Cost Types | 1 | 13_ACT | M.A. Wood | M.A. Wood |  | N/A | Initial Creation | Export/Import | Standard Transaction | 1 | G. Parisot | Yes | n/a | n/a | n/a
14 | CO | Allocation Cycles | Master Data | 12_Upload Ready to QAS/1 | 10 | No | Low | Cost Centers, Activity Types | 1 | 14 ALL_CYCLES | M.A. Wood | M.A. Wood |  | N/A | Initial Creation | Export/Import | Standard Transaction | 1 | G. Parisot | No | n/a | n/a | n/a
15 | PM | Equipments | Master Data | 11_Fixing in MIG/2 | 45000 | No | Very high | CO Objects, Business Partners, Assets, Functional Locations | 5 | 15_EQUIPMENT | S. A. Foster | I. Clendenning |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 25 | J. McCoffin | Yes | PM - Equipments | 2 | 8
16 | PM | Functional Locations | Master Data | 11_Fixing in MIG/2 | 11000 | No | High | Business Partners, Assets, Work Center, Projects, Settlement Rules | 4 | 16 FUNC LOC | S. A. Foster | I. Clendenning |  | XML (manual file creation) | Standard (Migrate Your Data) or Manually | Standard (Migrate Your Data) | Manually & Migrate Your Data | 17 | J. McCoffin | Yes | PM - Functional Locations | 2 | 8
17 | PM | Work Center | Master Data | 12_Upload Ready to QAS/1 | 100 | No | Low | Cost Centers, Activity Types, Tariffs | 2 | 17 Work Center | S. A. Foster | I. Clendenning |  | N/A | Initial Creation | Export/Import | Standard Transaction | 6 | J. McCoffin | No | n/a | 1 | 3
18 | MM | Materials | Master Data | 11_Fixing in MIG/2 | 9000 | No | Very high |  | 2 | 18 Material | R. Yang | W. Axmaker |  | XML (manual file creation) | Standard or Manually | Standard Upload using LTMC | Standard Upload using LTMC | 22 | D. Bookout | Yes | MM - Materials | 3 | 6
19 | TR | TRM Business Partner with Counterparty Role / General Data | Master Data | 12_Upload Ready to QAS/1 | 65 | No | Low | Business Partners | 3 | 19 BP Roles | J. Smith | V. Shiplet |  | Z-Program | Z-Table | Z-Program | Z-Program | 0.5 | T. Moorelock | No | ZTRBPR | 1 | 2
20 | TR | TRM Business Partner with Counterparty Role / Company Code | Master Data | 12_Upload Ready to QAS/1 | 65 | No | Low | Business Partners | 3 | 19 BP Roles | J. Smith | V. Shiplet |  | Z-Program | Z-Table | Z-Program | Z-Program | 0.5 | T. Moorelock | No | ZTRBPR | 1 | 2
21 | FI | Bank Master data | Master Data | 12_Upload Ready to QAS/1 | 4000 | Yes | Medium |  | 1 | 21 Bank MD | A. M. Hill | S. Dovalin |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 12 | J. Barela | Yes | FI - Bank Data | 1 | 6
22 | FI | Bank Accounts | Master Data | 11_Fixing in MIG/2 | 150 | Yes | Medium | GL Accounts, Bank Master Data, SAP Users | 2 | 22 Bank ACC | A. M. Hill | S. Dovalin |  | N/A | Initial Creation | Export/Import | Standard Transaction | 12 | J. Barela | Yes | n/a | 1 | 2
23 | FI | AR Open Items | Transactional Data | 10_OK in MIG/2 | 60000 | No | High | Business Partner, GL Accounts, CO Objects, FI-Characteristics | 3 | 23 AR OI | V. Long | S. Dovalin | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data | 20 | J. Barela | No | FI - OI AR | 4 | 20
24 | FI | AP Open Items | Transactional Data | 11_Fixing in MIG/2 | 55000 | No | High | Business Partner, GL Accounts, CO Objects, FI-Characteristics | 3 | 24 AP OI | V. Long | S. Dovalin | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data | 20 | W. Desegur | No | FI - OI AP | 4 | 20
25 | FI | GL Open Items | Transactional Data | 10_OK in MIG/2 | 800000 | No | High | GL Accounts, CO objects, FI-Characteristics | 3 | 25 GL OI | A. Green | S. Tigner | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data | 20 | W. Desegur | No | FI - OP GL | 4 | 20
26 | FI | GL Balances | Transactional Data | 11_Fixing in MIG/2 | 6000 | No | High | GL Accounts, FI-Characteristics | 3 | 26 Balance | A. Green | S. Tigner | A. Castree | Z-Program (Staging Table) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Staging & Migrate Your Data | 20 | J. Barela | No | FI - Balances | 4 | 20
27 | FI | Recurring Entries | Transactional Data | 12_Upload Ready to QAS/1 | 5000 | Yes | High | Business Partners, GL Accounts, CO Objects | 3 | 27 RE | V. Long | V. Long | B. Sheftall | Z-Program | Z-Table | Z-Program | Z-Program | 17 | W. Desegur | No | ZFIMIGRE | 2 | 6
28 | FI | Dispute Cases | Transactional Data | 9_Upload Ready to MIG/2 | 1000 | No | High | Business Partners, AR Open Items, SAP Users | 4 | 28 DC | V. Long | V. Long | B. Sheftall | Z-Program | Z-Table | Z-Program | Z-Program | 20 | J. Barela | No | ZFIMIGDPT | 2 | 8
29 | MM | Material Stock | Transactional Data | 11_Fixing in MIG/2 | 3000 | No | High | GL Accounts, Materials | 3 | 29 MM Stock | R. Yang | W. Axmaker |  | XML (manual file creation) | Standard or Manually | Standard Upload using LTMC | Standard Upload using LTMC | 20 | D. Bookout | No | MM - Material Stock | 3 | 4
30 | PM | Plant Maintenance Open Orders | Transactional Data | 9_Upload Ready to MIG/2 | 1500 | No | Very high | CO Objects, FI- Characteristics, Activity Types, Equipments, Functional Location, Materials, Work Centers, Work Schedules, Service Schedules, Notifications | 9 | 30 PM ORD | J. Hullet | I. Clendenning |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 22 | J. McCoffin | No | PM - PM Open Orders | 2 | 8
31 | PM | Measuring Points | Master Data | 11_Fixing in MIG/2 | 35000 | Yes | Medium | Equipments, Functional Locations | 6 | 31 MEASP | J. Hullet | I. Clendenning |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 13 | E. Ulibari | No | PM - Meas. Points | 1 | 4
32 | PM | Notifications | Master Data | 9_Upload Ready to MIG/2 | 14000 | Yes | Medium | Equipments, Functional Locations, Work Centers, Measuring Points | 7 | 32 NOT | J. Hullet | I. Clendenning |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 11 | E. Ulibari | No | PM - Notifications | 1 | 8
33 | PM | Measurenment Documents | Transactional Data | 9_Upload Ready to MIG/2 | 350000 | No | Medium | Equipments, Functional Locations, Mesuring Points, Notifications | 8 | 33 MEASD | J. Hullet | I. Clendenning |  | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Standard (Migrate Your Data) | Direct Transfer | 11 | E. Ulibari | No | PM - Meas. Documents | 1 | 13
34 | TR | Bank Guarantees | Transactional Data | 2_Design Clear | 130 | No | High | Business Partners, Facilities | 4 | 34 TR BGUAR | P. J. White | V. Shiplet | A. Castree | Z-Program | Z-Table | Z-Program | Z-Program | 16 | S. Oglebay | No | ZTRMIGBG | 1 | 8
35 | TR | Facilities | Transactional Data | 10_OK in MIG/2 | 15 | No | High | Business Partners | 3 | 35 TR FAC | P. J. White | V. Shiplet | B. Sheftall | Z-Program | Z-Table | Z-Program | Z-Program | 16 | S. Oglebay | No | ZTRMIGFAC | 1 | 1
36 | TR | IR Instruments | Transactional Data | 10_OK in MIG/2 | 100 | No | High | Business Partners | 3 | 36 TR IR INSTR | P. J. White | V. Shiplet | A. Castree | XML (manual file creation) | Standard (Migrate Your Data) or Manually | Standard (Migrate Your Data) | Manually & Migrate Your Data | 16 | S. Oglebay | No | TR - IR | 1 | 8
37 | PR | Open Purchase Orders | Transactional Data | 9_Upload Ready to MIG/2 | 9000 | No | Very high | Business Partners, GL Accounts, FI-Characteristics, PM Orders, Materialien, Purchasing Info Records | 10 | 37 OPO | K. Seabrook | W. Axmaker | B. Sheftall | XML (manual file creation) | Standard (Migrate Your Data) or Manually | Standard (Migrate Your Data) | Manually & Migrate Your Data | 25 | W. Uharriet | No | PR - Open PO | 4 | 8
38 | Claim | Claim Office | Transactional Data | 9_Upload Ready to MIG/2 | > 3,5 Mln | No | High | GL Accounts, FI Postings, Business Partners, Equipments, Functional Locations | 6 |  | A. J Miller | A. J Miller | A. J Miller | n/a | n/a | n/a | Client Program | n/a | A. J Miller | No | n/a | n/a | 16
…

## Input Help
Object Type:
1 | Master Data | Yes
2 | Transactional Data | No
SAP Modul:
1 | CO
2 | FI
3 | MM
4 | PM
5 | PR
6 | TR
7 | Claim
8 | PS
Object Migration Status:
1 | 1_New | New migration object
2 | 2_Design Clear | Migration design is identified
3 | 3_Implementation | Migration program is in implementation
4 | 4_Test | Migration program is under testing
5 | 5_Fixing | Bugs have been identified and are being corrected
6 | 6_Ready | Migration program is technically ready. Data sample can be uploaded to MIG/1
7 | 7_OK in MIG/1 | Migration of the data sample to MIG/1 is successful. The migrated data is basically OK
8 | 8_Fixing in MIG/1 | Bugs have been identified in MIG/1 and are being corrected
9 | 9_Upload Ready to MIG/2 | Bugs were corrected. Data is ready for upload to MIG/2
10 | 10_OK in MIG/2 | Migration of all data to MIG/2 is successful, even if the selection criteria are insufficient. The completeness of data transfer is more than 80%. The migrated data is basically OK. The SAP Test Load was successful
11 | 11_Fixing in MIG/2 | Bugs have been identified in MIG/2 and are being corrected
12 | 12_Upload Ready to QAS/1 | Bugs were corrected. Data is ready for upload to QAS/1
13 | 13_OK in QAS/1 | Migration of all data to QAS/1 was successful. The completeness of data transfer is 100%. The migrated data is basically OK
14 | 14_Fixing in QAS/1 | Bugs have been identified in QAS/1 and are being corrected
15 | 15_Upload Ready to QAS/1 | Bugs were corrected. Data is ready for upload to QAS/2
16 | 16_OK in QAS/2 | Migration of all data to QAS/2 was successful. The completeness of data transfer is 100%. Migrated data quality meets customer requirenments. The data was accepted by the client. The migration was predominantely carried out within scheduled time frame
17 | 17_Fixing in QAS/2 | Bugs have been identified in QAS/2 and are being corrected
18 | 18_Upload Ready to QAS/3 | Bugs were corrected. Data is ready for upload to QAS/3
19 | 19_OK in QAS/3 | Migration of all data to QAS/3 was successful. The completeness of data transfer is 100%. Migrated data quality meets customer requirenments. The migration was carried out within scheduled time frame
20 | 20_Production Load Ready | Data is ready for upload to productive system
21 | 21_In Acceptance | Migration of all data to Productive System was successful. Migrated data is accepted by the client
22 | 22_OK in Productive System | Acceptance Protocols were assigned by both sides (implementation partner and client). The migration of object has finished
Data Complexity:
1 | Very high
2 | High
3 | Medium
4 | Low