## Data Migration Test Plans
Data Migration Test Plans
|  |  | Project | New Implementation of S/4HAHA 2020 at XXXXX
|  |  | Workstream Lead | Aleksei Arziaev
|  |  | Goals of Data Migration Tests | Data Migration Test 1 (M1) - Verifying the effectiveness of the selected migration approach
Data Migration Test 2 (M2) - Attempting to migrate all data to identify exceptions, determining the time required for migration, and verifying the sequence of data migration
Data Migration Test 3 (M3) - Ensuring 100 percent of migrated data, clarifying the timing and sequence of object migtaion
Data Migration Test 4 (M4) - Ensuring data quality and meeting established migration deadlines
Data Migration Test 5 (M5) - Testing of data migration within the ambit of the Cutover Test Plan and data acceptance procedure
|  |  | Calendar Plan | Hyperlink Calendar Plan
|  |  | Data Migtaion Status | Hyperlink Data Migration Status | [11 empty] | Go to the Current Day:
|  |  | Cutover Test Plan | Hyperlink Cutover Test Plan | [11 empty] | #N/A | April 23 | [6 empty] | April 23 | [6 empty] | April 23 | [6 empty] | April 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | May 23 | [6 empty] | June 23 | [6 empty] | June 23 | [6 empty] | June 23 | [6 empty] | June 23 | [6 empty] | July 23 | [6 empty] | July 23 | [6 empty] | July 23 | [6 empty] | July 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | August 23 | [6 empty] | September 23 | [6 empty] | September 23 | [6 empty] | September 23 | [6 empty] | September 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | October 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | November 23 | [6 empty] | December 23 | [6 empty] | December 23 | [6 empty] | December 23 | [6 empty] | December 23 | [6 empty] | January 24 | [6 empty] | January 24 | [6 empty] | January 24 | [6 empty] | January 24 | [6 empty] | January 24 | [6 empty] | February 24 | [6 empty] | February 24 | [6 empty] | February 24 | [6 empty] | February 24 | [6 empty] | March 24 | [6 empty] | March 24 | [6 empty] | March 24 | [6 empty] | March 24
|  |  | Data Verification | Hyperlink Data Verification Protocols | [11 empty] | Start of the Calendar: | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13
|  |  | Data Acceptance Test | Hyperlink Data Acceptance Test Forms | [11 empty] | 2023-04-01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Modul | Mig. Test | Line | Data Migration Activity | Dependencies | Data Migration Runbook (Hyperlink) | Start [DD/MM/YYYY] | Start Time [GMT+02.00] | Finish [DD/MM/YYYY] | Finish Time [GMT+02.00] | Status [0 bis 100] | Milestone [DD/MM/YYYY] | Finished [f] | Migration Consultant | Representative | Reviewer | Commentary | time axis 2023-04-01 to 2024-03-29
| M1 | x | Data Migration Test 1 |  |  | 2023-04-03 | 9:00 | 2023-04-30 | 17:00
| M1 | x | Week 1 |  |  | 2023-04-03 | 9:00 | 2023-04-07 | 17:00
CO | M1 |  | Verification of transported CO Objects and hierarchies |  | Folder_CO_Objects | 2023-04-03 | 9:00 | 2023-04-03 | 12:00 | 100% | 2023-04-03 | f |  |  | According Data Object Migration Cards
CO | M1 |  | Upload of Projects and Setting the Status "REL" | FI Characteristics | 12_M_Runbook_PR_M1 | 2023-04-03 | 12:00 | 2023-04-03 | 17:00 | 100% | 2023-04-03 | f | M.A. Wood | A. Castree | G. Parisot
FI | M1 |  | Migration of G/L Accounts and Secondary Cost Types |  | 2_M_Runbook_GL_M1 | 2023-04-03 | 9:00 | 2023-04-03 | 17:00 | 100% | 2023-04-03 | f | S. Dovalin | A. Green | J. Barela
CO | M1 |  | Direct Transfer of Statistical Internal Orders | FI Characteristics, Cost Centers | 6_M_Runbook_ST_ORD_M1 | 2023-04-04 | 13:00 | 2023-04-04 | 17:00 | 99% | 2023-04-04 | f | S. Dovalin | M.A. Wood | G. Parisot
TR | M1 |  | Direkt Transfer Bank Master Data |  | 21_M_Runbook_BANK_M1 | 2023-04-03 | 9:00 | 2023-04-04 | 17:00 | 100% | 2023-04-04 | f | S. Dovalin | A. M. Hill | J. Barela
TR | M1 |  | Import of Bank Accounts | GL Accounts, Bank Master Data | 22_M_Runbook_BANK_ACC_M1 | 2023-04-05 | 9:00 | 2023-04-06 | 17:00 | 100% | 2023-04-06 | f | S. Dovalin | A. M. Hill | J. Barela
PM | M1 |  | Direct Transfer of Characteristics |  | 40_M_Runbook_CHAR_M1 | 2023-04-04 | 8:00 | 2023-04-05 | 17:00 | 100% | 2023-04-05 | f | B. Sheftall | S. A. Foster | W. Hendrix
PM | M1 |  | Upload of Work Centers | Cost Centers, Activity Types, Tariffs | 17_M_Runbook_WC_M1 | 2023-04-05 | 8:00 | 2023-04-05 | 17:00 | 100% | 2023-04-05 | f | I. Clendenning | S. A. Foster | J. McCoffin
MM | M1 |  | Upload of Materials |  | 18_M_Runbook_MAT_M1 | 2023-04-03 | 13:00 | 2023-04-05 | 17:00 | 100% | 2023-04-05 | f | W. Axmaker | R. Yang | D. Bookout
MM | M1 |  | Upload of Material Stock | MM Master Data, GL Accounts | 29_M_Runbook_MAT_STC_M1 | 2023-04-06 | 8:00 | 2023-04-07 | 17:00 | 100% | 2023-04-07 | f | W. Axmaker | R. Yang | D. Bookout
PM | M1 |  | Direct Transfer of Classes | Characteristics | 39_M_Runbook_CLASS_M1 | 2023-04-06 | 8:00 | 2023-04-07 | 17:00 | 100% | 2023-04-07 | f | I. Clendenning | S. A. Foster | K. Monroe
| M1 | x | Week 2 |  |  | 2023-04-10 | 8:00 | 2023-04-14 | 17:00
FI | M1 |  | Migration of Business Partners | GL Accounts, Bank Master Data, Bank Accounts | 1_M_Runbook_BP_M1 | 2023-04-10 | 8:00 | 2023-04-13 | 17:00 | 100% | 2023-04-13 | f | S. Dovalin | J. Smith | T. Moorelock
FI | M1 |  | Migration of GL Open Items | GL Accounts, CO Objects, FI Characteristics | 25_M_Runbook_GL_OI_M1 | 2023-04-10 | 8:00 | 2023-04-12 | 17:00 | 100% | 2023-04-12 | f | S. Tigner | A. Green | W. Desegur
FI | M1 |  | Migration of GL Open Items (Ledger Group Spec.) | GL Accounts, CO objects, FI Characteristics | 25_M_Runbook_GL_OI_M1 | 2023-04-13 | 8:00 | 2023-04-14 | 17:00 | 100% | 2023-04-14 | f | S. Tigner | A. Green | J. Thomson
PM | M1 |  | Migration of Task List | CO Objects, FI Characteristics, Activity Types, Strategies | 42_M_Runbook_TASK_M1 | 2023-04-10 | 8:00 | 2023-04-11 | 17:00 | 100% | 2023-04-11 | f | C. Frank | S. Nilson | M. Muller
TR | M1 |  | Creation of General Data and Roles for TRM Business Partner | Business Partners | 19_M_Runbook_BP_TR_M1 | 2023-04-14 | 8:00 | 2023-04-14 | 12:00 | 100% | 2023-04-14 | f | V. Shiplet | J. Smith | T. Moorelock
TR | M1 |  | Creation of Company Code Data for TRM Business Partner | Business Partners | 20_M_Runbook_BP_TR_M1 | 2023-04-14 | 13:00 | 2023-04-14 | 17:00 | 100% | 2023-04-14 | f | V. Shiplet | J. Smith | T. Moorelock
TR | M1 |  | Direct Transfer of SEPA Mandate | Business Partners with Customer Role | 5_M_Runbook_SEPA_M1 | 2023-04-14 | 8:00 | 2023-04-14 | 17:00 | 100% | 2023-04-14 | f | S. Dovalin | A. Green | J. Barela
| M1 | X | Week 3 |  |  | 2023-04-17 | 8:00 | 2023-04-21 | 17:00
FI | M1 |  | Migration of Assets and Transactional Data | GL Accounts, Internal Orders, Cost Centers, Business Partners | 3_M_Runbook_AST_M1 4_M_Runbook_AST_TR_M1 | 2023-04-17 | 8:00 | 2023-04-20 | 17:00 | 100% | 2023-04-20 | f | S. Tigner | A. Castree | A. Lolmaugh
FI | M1 |  | Migration of AR Open Items | Business Partner, GL Accounts, CO Objects, FI Characteristics | 23_M_Runbook_AR_OI_M1 | 2023-04-17 | 8:00 | 2023-04-19 | 12:00 | 100% | 2023-04-19 | f | A. Castree | S. Dovalin | J. Barela
FI | M1 |  | Migration of AP Open Items | Business Partner, GL Accounts, CO Objects, FI Characteristics | 24_M_Runbook_AP_OI_M1 | 2023-04-19 | 13:00 | 2023-04-21 | 17:00 | 100% | 2023-04-21 | f | S. Dovalin | A. Castree | W. Desegur
FI | M1 |  | Transfer of Recurring Entries | Business Partners, GL Accounts, CO Objects, FI Characteristics | 27_M_Runbook_RE_M1 | 2023-04-17 | 8:00 | 2023-04-18 | 17:00 | 100% | 2023-04-18 | f | V. Long | B. Sheftall | W. Desegur
TR | M1 |  | Transfer of Facilities | Business Partners | 35_M_Runbook_FAC_M1 | 2023-04-17 | 8:00 | 2023-04-18 | 17:00 | 100% | 2023-04-18 | f | V. Shiplet | P. J. White | S. Oglebay
TR | M1 |  | Transfer of Bank Guarantees | Business Partners, Facilities | 34_M_RUNBOOK_BANK_GRT_M1 | 2023-04-19 | 8:00 | 2023-04-20 | 17:00 | 100% | 2023-04-20 | f | V. Shiplet | P. J. White | S. Oglebay
TR | M1 |  | Migration of IR Instruments | Business Partners | 36_M_Runbook_IR_M1 | 2023-04-21 | 8:00 | 2023-04-21 | 17:00 | 100% | 2023-04-21 | f | V. Shiplet | P. J. White | S. Oglebay
PM | M1 |  | Migration of Functional Location | Work Center, PSP-Elements, Settlement Rules, Business Partners, Assets, Cost Centers | 16_M_Runbook_FUN_LOC_M1 | 2023-04-17 | 8:00 | 2023-04-18 | 17:00 | 100% | 2023-04-18 | f | I. Clendenning | S. A. Foster | J. McCoffin
PM | M1 |  | Direct Transfer of Customer Material Info Records | Business Partners, Materials | 43_M_Runbook_CUS_M_INFO_M1 | 2023-04-18 | 8:00 | 2023-04-19 | 17:00 | 100% | 2023-04-19 | f | W. Axmaker | R. Yang | H. Packard
PM | M1 |  | Direct Transfer of Equipments | CO Objects, Business Partners, Assets, Functional Locations | 15_M_Runbook_EQP_M1 | 2023-04-19 | 8:00 | 2023-04-20 | 17:00 | 100% | 2023-04-20 | f | I. Clendenning | S. A. Foster | J. McCoffin
FI | M1 |  | Transfer of Dispute Cases | Business Partners, AR Open Items | 28_M_Runbook_DCASE_M1 | 2023-04-17 | 8:00 | 2023-04-19 | 17:00 | 100% | 2023-04-19 | f | V. Long | B. Sheftall | J. Barela
FI | M1 |  | Migration of GL Balances | GL Accounts, FI Characteristics | 26_M_Runbook_GL_BLC_M1 | 2023-04-17 | 8:00 | 2023-04-20 | 17:00 | 100% | 2023-04-20 | f | S. Tigner | A. Green | J. Barela
CO | M1 |  | Migration of PL Balances | GL Accounts, Cost Centers, FI Characteristics | 41_M_Runbook_PL_BLC_M1 | 2023-04-21 | 9:00 | 2023-04-21 | 13:00 | 100% | 2023-04-21 | f | V. Long | A. Castree | S. Luis
PM | M1 |  | Direct Transfer of Measuring Points | Equipments, Functional Locations | 31_M_Runbook_MEASP_M1 | 2023-04-21 | 8:00 | 2023-04-21 | 17:00 | 100% | 2023-04-21 | f | I. Clendenning | J. Hullet | E. Ulibari
| M1 | X | Week 4 |  |  | 2023-04-24 | 8:00 | 2023-04-28 | 17:00
Calim | M1 |  | Migratioon of Claim Office | GL Accounts, FI Postings, Business Partners, Equipments, Functional Locations | n/a | 2024-04-24 | 8:00 | 2023-04-26 | 17:00 | 100% | 2023-04-26 | f | A. J Miller | A. J Miller | A. J Miller
PM | M1 |  | Direct Transfer of Notifications | Equipments, Functional Locations, Work Centers, Measuring Points | 32_M_Runbook_NOT_M1 | 2024-04-24 | 8:00 | 2023-04-24 | 17:00 | 100% | 2023-04-24 | f | I. Clendenning | J. Hullet | E. Ulibari
PM | M1 |  | Migration of Maintenance Plans | Equipments, Functional Locations, Work Centers, Materials, Task Lists | 37_M_Runbook_PMP_M1 | 2023-04-24 | 8:00 | 2023-04-25 | 17:00 | 100% | 2023-04-25 | f | I. Clendenning | J. Hullet | J. McCoffin
PM | M1 |  | Direct Transfer of Object Classification | Materials, Equipments, Functional Locations, Notifications, Classes, Characteristics | 44_M_Runbook_OBJ_CLASS_M1 | 2023-04-26 | 8:00 | 2023-04-27 | 12:00 | 100% | 2023-04-27 | f | I. Clendenning | S. A. Foster | K. Monroe
PM | M1 |  | Direct Transfer of Plant Maintenance Open Orders | CO Objects, FI- Characteristics, Activity Types, Equipments, Functional Location, Materials, Work Centers, Notifications | 30_M_Runbook_PM_ORD_M1 | 2023-04-25 | 8:00 | 2023-04-26 | 17:00 | 100% | 2023-04-26 | f | I. Clendenning | S. A. Foster | K. Monroe
PM | M1 |  | Direct Transfer of Measurenment Documents | Equipments, Functional Locations, Mesuring Points, Notifications | 33_M_Runbook_MEAS_DOC_M1 | 2023-04-27 | 13:00 | 2023-04-28 | 17:00 | 100% | 2023-04-28 | f | I. Clendenning | J. Hullet | E. Ulibari
PR | M1 |  | Upload of Open Purchase Orders | Business Partners, CO Objects, PM Orders, MM Master Data, FI Characteristics, GL Accounts, AP Open Items | 37_M_Runbook_OPO_M1 | 2023-04-27 | 8:00 | 2023-04-28 | 17:00 | 100% | 2023-04-28 | f | W. Axmaker | K. Seabrook | W. Uharriet
| M3 | X | Data Migration Test 3 |  |  | 2023-07-17 | 8:00 | 2023-08-04 | 17:00
| M3 | X | Week 1 |  |  | 2023-07-17 | 8:00 | 2023-07-21 | 17:00
CO | M3 |  | Verification of transported CO Objects and hierarchies |  | Folder_CO_Objects | 2023-07-17 | 8:00 | 2023-07-17 | 10:00 | 100% | 2023-07-17 | f |  |  | According Data Object Migration Cards
FI | M3 |  | Migration of G/L Accounts and Secondary Cost Types |  | 2_M_Runbook_GL_M3 | 2023-07-17 | 8:00 | 2023-07-17 | 10:00 | 100% | 2023-07-17 | f | S. Dovalin | A. Green | J. Barela
CO | M3 |  | Upload of Projects and Setting the Status "REL" | FI Characteristics | 12_M_Runbook_PR_M3 | 2023-07-17 | 10:00 | 2023-07-17 | 12:00 | 100% | 2023-07-17 | f | M.A. Wood | A. Castree | G. Parisot
FI | M3 |  | Direkt Transfer of Bank Master Data |  | 21_M_Runbook_BANK_M3 | 2023-07-17 | 8:00 | 2023-07-17 | 15:00 | 100% | 2023-07-17 | f | S. Dovalin | A. M. Hill | J. Barela
CO | M3 |  | Direct Transfer of Statistical Internal Orders | FI Characteristics, Cost Centers | 6_M_Runbook_ST_ORD_M3 | 2023-07-17 | 10:00 | 2023-07-17 | 14:00 | 100% | 2023-07-17 | f | S. Dovalin | M.A. Wood | G. Parisot
MM | M3 |  | Upload of Materials |  | 18_M_Runbook_MAT_M3 | 2023-07-17 | 10:00 | 2023-07-17 | 17:00 | 100% | 2023-07-17 | f | W. Axmaker | R. Yang | D. Bookout
PM | M3 |  | Upload of Work Centers | Cost Centers, Activity Types, Tariffs | 17_M_Runbook_WC_M3 | 2023-07-17 | 13:00 | 2023-07-17 | 16:00 | 100% | 2023-07-17 | f | I. Clendenning | S. A. Foster | J. McCoffin
TR | M3 |  | Import of Bank Accounts | GL Accounts, Bank Master Data | 22_M_Runbook_BANK_ACC_M3 | 2023-07-17 | 15:00 | 2023-07-17 | 17:00 | 100% | 2023-07-17 | f | S. Dovalin | A. M. Hill | J. Barela
FI | M3 |  | Migration of Business Partners | GL Accounts, Bank Master Data, Bank Accounts | 1_M_Runbook_BP_M3 | 2023-07-18 | 8:00 | 2023-07-20 | 17:00 | 100% | 2023-07-20 | f | S. Dovalin | J. Smith | T. Moorelock
PM | M3 |  | Direct Transfer of Characteristics |  | 40_M_Runbook_CHAR_M3 | 2023-07-18 | 8:00 | 2023-07-18 | 12:00 | 100% | 2023-07-18 | f | B. Sheftall | S. A. Foster | W. Hendrix
PM | M3 |  | Migration of Task Lists | CO Objects, FI Characteristics, Activity Types, Strategies | 42_M_Runbook_TASK_M3 | 2023-07-18 | 13:00 | 2023-07-18 | 17:00 | 100% | 2023-07-18 | f | C. Frank | S. Nilson | M. Muller
PM | M3 |  | Direct Transfer of Classes | Characteristics | 39_M_Runbook_CLASS_M3 | 2023-07-19 | 8:00 | 2023-07-19 | 12:00 | 100% | 2023-07-19 | f | I. Clendenning | S. A. Foster | K. Monroe
MM | M3 |  | Upload of Material Stock | MM Master Data, GL Accounts | 29_M_Runbook_MAT_STC_M3 | 2023-07-19 | 8:00 | 2023-07-19 | 12:00 | 100% | 2023-07-19 | f | W. Axmaker | R. Yang | D. Bookout
TR | M3 |  | Creation of General Data and Roles for TRM Business Partner | Business Partners | 19_M_Runbook_BP_TR_M3 | 2023-07-21 | 8:00 | 2023-07-21 | 10:00 | 100% | 2023-07-21 | f | V. Shiplet | J. Smith | T. Moorelock
TR | M3 |  | Creation of Company Code Data for TRM Business Partner | Business Partners | 20_M_Runbook_BP_TR_M3 | 2023-07-21 | 10:00 | 2023-07-21 | 12:00 | 100% | 2023-07-21 | f | V. Shiplet | J. Smith | T. Moorelock
TR | M3 |  | Direct Transfer of SEPA Mandate | Business Partners with Customer Role | 5_M_Runbook_SEPA_M3 | 2023-07-21 | 13:00 | 2023-07-21 | 17:00 | 100% | 2023-07-21 | f | S. Dovalin | A. Green | J. Barela
PM | M3 |  | Direct Transfer of Customer Material Info Records | Business Partners, Materials | 43_M_Runbook_CUS_M_INFO_M3 | 2023-07-21 | 8:00 | 2023-07-21 | 15:00 | 100% | 2023-07-21 | f | W. Axmaker | R. Yang | H. Packard
| M3 | X | Week 2 |  |  | 2023-07-24 | 8:00 | 2023-07-28 | 17:00
FI | M3 |  | Migration of Main Assets and Transactional Data | GL Accounts, Internal Orders, Cost Centers, Business Partners | 3_M_Runbook_AST_M3 4_M_Runbook_AST_TR_M3 | 2023-07-24 | 8:00 | 2023-07-25 | 17:00 | 100% | 2023-07-25 | f | S. Tigner | A. Castree | A. Lolmaugh
FI | M3 |  | Migration of Sub-Assets and Transactional Data | Assets, GL Accounts, Internal Orders, Cost Centers, Business Partners | 3_M_Runbook_AST_M3 4_M_Runbook_AST_TR_M3 | 2023-07-26 | 8:00 | 2023-07-26 | 17:00 | 100% | 2023-07-26 | f | S. Tigner | A. Castree | A. Lolmaugh
FI | M3 |  | Migration of AR Open Items | Business Partner, GL Accounts, CO Objects, FI Characteristics | 23_M_Runbook_AR_OI_M3 | 2023-07-24 | 8:00 | 2023-07-26 | 12:00 | 100% | 2023-07-26 | f | A. Castree | S. Dovalin | J. Barela
FI | M3 |  | Migration of AP Open Items | Business Partner, GL Accounts, CO Objects, FI Characteristics | 24_M_Runbook_AP_OI_M3 | 2023-07-24 | 8:00 | 2023-07-26 | 12:00 | 100% | 2023-07-26 | f | S. Dovalin | A. Castree | W. Desegur
FI | M3 |  | Migration of GL Open Items | GL Accounts, CO Objects, FI Characteristics | 25_M_Runbook_GL_OI_M3 | 2023-07-24 | 8:00 | 2023-07-26 | 12:00 | 100% | 2023-07-26 | f | S. Tigner | A. Green | W. Desegur
FI | M3 |  | Migration of GL Open Items (Ledger Group Spec.) | GL Accounts, CO objects, FI Characteristics | 25_M_Runbook_GL_OI_M3 | 2023-07-26 | 13:00 | 2023-07-27 | 17:00 | 100% | 2023-07-27 | f | S. Tigner | A. Green | J. Thomson
FI | M3 |  | Migration of GL Balances | GL Accounts, FI Characteristics | 26_M_Runbook_GL_BLC_M3 | 2023-07-27 | 8:00 | 2023-07-28 | 17:00 | 100% | 2023-07-28 | f | S. Tigner | A. Green | J. Barela
PM | M3 |  | Migration of Functional Locations | Work Center, PSP-Elements, Settlement Rules, Business Partners, Assets, Cost Centers | 16_M_Runbook_FUN_LOC_M3 | 2023-07-27 | 8:00 | 2023-07-27 | 17:00 | 100% | 2023-07-27 | f | I. Clendenning | S. A. Foster | J. McCoffin
TR | M3 |  | Transfer of Facilities | Business Partners | 35_M_Runbook_FAC_M3 | 2023-07-24 | 8:00 | 2023-07-24 | 9:00 | 100% | 2023-07-24 | f | V. Shiplet | P. J. White | S. Oglebay
PM | M3 |  | Direct Transfer of Equipments | CO Objects, Business Partners, Assets, Functional Locations | 15_M_Runbook_EQP_M3 | 2023-07-28 | 8:00 | 2023-07-28 | 17:00 | 100% | 2023-07-28 | f | I. Clendenning | S. A. Foster | J. McCoffin
FI | M3 |  | Transfer of Recurring Entries | Business Partners, GL Accounts, CO Objects, FI Characteristics | 27_M_Runbook_RE_M3 | 2023-07-25 | 8:00 | 2023-07-25 | 14:00 | 99.9% | 2023-07-25 | f | V. Long | B. Sheftall | W. Desegur
TR | M3 |  | Transfer of Bank Guarantees | Business Partners, Facilities | 34_M_RUNBOOK_BANK_GRT_M3 | 2023-07-24 | 9:00 | 2023-07-24 | 17:00 | 100% | 2023-07-24 | f | V. Shiplet | P. J. White | S. Oglebay
TR | M3 |  | Migration of IR Instruments | Business Partners | 36_M_Runbook_IR_M3 | 2023-07-25 | 8:00 | 2023-07-25 | 17:00 | 100% | 2023-07-25 | f | V. Shiplet | P. J. White | S. Oglebay
FI | M3 |  | Transfer of Dispute Cases | Business Partners, AR Open Items, SAP Users | 28_M_Runbook_DCASE_M3 | 2023-07-28 | 8:00 | 2023-07-28 | 17:00 | 100% | 2023-07-28 | f | V. Long | B. Sheftall | J. Barela
| M3 | X | Week 3 |  |  | 2023-07-31 | 8:00 | 2023-08-04 | 12:00
Calim | M3 |  | Migratioon of Claim Office | GL Accounts, FI Postings, Business Partners, Equipments, Functional Locations | n/a | 2023-07-31 | 8:00 | 2023-08-01 | 17:00 | 100% | 2023-08-01 | f | A. J Miller | A. J Miller | A. J Miller
CO | M3 |  | Migration of PL Balances | GL Accounts, Cost Centers, FI Characteristics | 41_M_Runbook_PL_BLC_M3 | 2023-07-31 | 8:00 | 2023-07-31 | 12:00 | 100% | 2023-07-31 | f | V. Long | A. Castree | S. Luis
PM | M3 |  | Direct Transfer of Measuring Points | Equipments, Functional Locations | 31_M_Runbook_MEASP_M3 | 2023-07-31 | 8:00 | 2023-07-31 | 12:00 | 100% | 2023-07-31 | f | I. Clendenning | J. Hullet | E. Ulibari
PM | M3 |  | Migration of Maintenance Plans | Equipments, Functional Locations, Work Centers, Materials, Task Lists | 37_M_Runbook_PMP_M3 | 2023-07-31 | 8:00 | 2023-07-31 | 17:00 | 100% | 2023-07-31 | f | I. Clendenning | J. Hullet | J. McCoffin
PM | M3 |  | Direct Transfer of Notifications | Equipments, Functional Locations, Work Centers, Measuring Points | 32_M_Runbook_NOT_M3 | 2023-08-01 | 8:00 | 2023-08-01 | 17:00 | 100% | 2023-08-01 | f | I. Clendenning | J. Hullet | E. Ulibari
PM | M3 |  | Direct Transfer of Plant Maintenance Open Orders | CO Objects, FI Characteristics, Activity Types, Equipments, Functional Location, Materials, Work Centers, Work Schedules, Service Schedules, Notifications | 30_M_Runbook_PM_ORD_M3 | 2023-08-02 | 8:00 | 2023-08-02 | 17:00 | 100% | 2023-08-02 | f | I. Clendenning | S. A. Foster | K. Monroe
PM | M3 |  | Direct Transfer of Measurenment Documents | Equipments, Functional Locations, Mesuring Points, Notifications | 33_M_Runbook_MEAS_DOC_M3 | 2023-08-03 | 8:00 | 2023-08-04 | 12:00 | 100% | 2023-08-04 | f | I. Clendenning | J. Hullet | E. Ulibari
PM | M3 |  | Direct Transfer of Object Classification | Materials, Equipments, Functional Locations, Notifications, Classes, Characteristics | 44_M_Runbook_OBJ_CLASS_M3 | 2023-08-03 | 8:00 | 2023-08-03 | 17:00 | 100% | 2023-08-03 | f | B. Sheftall | S. A. Foster | W. Hendrix
PR | M3 |  | Upload of Open Purchase Orders | Business Partners, CO Objects, PM Orders, MM Master Data, FI Characteristics, GL Accounts, AP Open Items | 37_M_Runbook_OPO_M3 | 2023-08-03 | 8:00 | 2023-08-03 | 17:00 | 100% | 2023-08-03 | f | W. Axmaker | K. Seabrook | W. Uharriet
| M5 | X | Data Migration Test 5 (the Part of the Cutover Test) |  |  | 2023-10-23 | 8:00 | 2023-11-10 | 17:00
| M5 | X | Week 1 |  |  | 2023-10-23 | 8:00 | 2023-10-27 | 17:00
CO | M5 |  | Acceptance of CO Objects |  |  | 2023-10-23 | 8:00 | 2023-10-23 | 17:00 | 100% | 2023-10-25 | f |  |  | According Data Object Migration Cards
FI | M5 |  | Migration of G/L Accounts and Cost Types |  | 2_M_Runbook_GL_M5 | 2023-10-23 | 8:00 | 2023-10-23 | 10:00 | 100% | 2023-10-23 | f | S. Dovalin | A. Green
FI | M5 |  | Acceptance of GL Accounts and Cost Types |  |  | 2023-10-23 | 10:00 | 2023-10-24 | 17:00 | 100% | 2023-10-24 | f |  |  | J. Barela
CO | M5 |  | Upload of Projects and Setting the Status "REL" | FI Characteristics | 12_M_Runbook_PR_M5 | 2023-10-23 | 10:00 | 2023-10-23 | 12:00 | 100% | 2023-10-23 | f | M.A. Wood | A. Castree
CO | M5 |  | Acceptance of Projects |  |  | 2023-10-23 | 12:00 | 2023-10-23 | 17:00 | 100% | 2023-10-23 | f |  |  | G. Parisot
FI | M5 |  | Direkt Transfer of Bank Master Data |  | 21_M_Runbook_BANK_M5 | 2023-10-23 | 8:00 | 2023-10-23 | 15:00 | 100% | 2023-10-23 | f | S. Dovalin | A. M. Hill
FI | M5 |  | Acceptance of Bank Master Data |  |  | 2023-10-23 | 15:00 | 2023-10-24 | 17:00 | 100% | 2023-10-24 | f |  |  | J. Barela
CO | M5 |  | Direct Transfer of Statistical Internal Orders | FI Characteristics, Cost Centers | 6_M_Runbook_ST_ORD_M5 | 2023-10-23 | 10:00 | 2023-10-23 | 14:00 | 100% | 2023-10-23 | f | S. Dovalin | M.A. Wood
CO | M5 |  | Acceptance of Statistical Internal Orders |  |  | 2023-10-23 | 14:00 | 2023-10-25 | 17:00 | 100% | 2023-10-25 | f |  |  | G. Parisot
MM | M5 |  | Upload of Materials |  | 18_M_Runbook_MAT_M5 | 2023-10-23 | 10:00 | 2023-10-23 | 17:00 | 100% | 2023-10-23 | f | W. Axmaker | R. Yang
MM | M5 |  | Acceptance of Materials |  |  | 2023-10-24 | 8:00 | 2023-10-25 | 17:00 | 100% | 2023-10-25 | f |  |  | D. Bookout
PM | M5 |  | Upload of Work Centers | Cost Centers, Activity Types, Tariffs | 17_M_Runbook_WC_M5 | 2023-10-23 | 13:00 | 2023-10-23 | 16:00 | 100% | 2023-10-23 | f | I. Clendenning | S. A. Foster
PM | M5 |  | Acceptnace of Work Centers |  |  | 2023-10-23 | 16:00 | 2023-10-23 | 17:00 | 100% | 2023-10-23 | f |  |  | J. McCoffin
TR | M5 |  | Import of Bank Accounts | GL Accounts, Bank Master Data | 22_M_Runbook_BANK_ACC_M5 | 2023-10-23 | 15:00 | 2023-10-23 | 17:00 | 100% | 2023-10-23 | f | S. Dovalin | A. M. Hill
TR | M5 |  | Acceptance of Bank Accounts |  |  | 2023-10-24 | 8:00 | 2023-10-24 | 12:00 | 100% | 2023-10-24 | f |  |  | J. Barela
FI | M5 |  | Migration of Business Partners | GL Accounts, Bank Master Data, Bank Accounts | 1_M_Runbook_BP_M5 | 2023-10-24 | 8:00 | 2023-10-26 | 17:00 | 100% | 2023-10-26 | f | S. Dovalin | J. Smith
FI | M5 |  | Acceptance of Business Partners |  |  | 2023-10-27 | 8:00 | 2023-10-31 | 17:00 | 100% | 2023-10-31 | f |  |  | T. Moorelock
PM | M5 |  | Direct Transfer of Characteristics |  | 40_M_Runbook_CHAR_M5 | 2023-10-24 | 8:00 | 2023-10-24 | 12:00 | 100% | 2023-10-24 | f | B. Sheftall | S. A. Foster
PM | M5 |  | Acceptance of Caharacteristics |  |  | 2023-10-24 | 13:00 | 2023-10-24 | 17:00 | 100% | 2023-10-24 | f |  |  | W. Hendrix
PM | M5 |  | Migration of Task Lists | CO Objects, FI Characteristics, Activity Types, Strategies | 42_M_Runbook_TASK_M5 | 2023-10-24 | 13:00 | 2023-10-24 | 17:00 | 100% | 2023-10-24 | f | C. Frank | S. Nilson
PM | M5 |  | Acceptance of Task Lists |  |  | 2023-10-25 | 8:00 | 2023-10-25 | 12:00 | 100% | 2023-10-25 | f |  |  | M. Muller
PM | M5 |  | Direct Transfer of Classes | Characteristics | 39_M_Runbook_CLASS_M5 | 2023-10-25 | 8:00 | 2023-10-25 | 12:00 | 100% | 2023-10-25 | f | I. Clendenning | S. A. Foster
PM | M5 |  | Acceptance of Classes |  |  | 2023-10-25 | 13:00 | 2023-10-25 | 17:00 | 100% | 2023-10-25 | f |  |  | K. Monroe
MM | M5 |  | Upload of Material Stock | MM Master Data, GL Accounts | 29_M_Runbook_MAT_STC_M5 | 2023-10-25 | 8:00 | 2023-10-25 | 12:00 | 100% | 2023-10-25 | f | W. Axmaker | R. Yang
MM | M5 |  | Acceptance of Material Stock |  |  | 2023-10-25 | 13:00 | 2023-10-25 | 17:00 | 100% | 2023-10-25 | f |  |  | D. Bookout
TR | M5 |  | Creation of General Data and Roles for TRM Business Partner | Business Partners | 19_M_Runbook_BP_TR_M5 | 2023-10-27 | 8:00 | 2023-10-27 | 10:00 | 100% | 2023-10-27 | f | V. Shiplet | J. Smith
TR | M5 |  | Creation of Company Code Data for TRM Business Partner | Business Partners | 20_M_Runbook_BP_TR_M5 | 2023-10-27 | 10:00 | 2023-10-27 | 12:00 | 100% | 2023-10-27 | f | V. Shiplet | J. Smith
TR | M5 |  | Acceptance of Business Partner Roles |  |  | 2023-10-27 | 13:00 | 2023-10-27 | 17:00 | 100% | 2023-10-27 | f |  |  | T. Moorelock
TR | M5 |  | Direct Transfer of SEPA Mandate | Business Partners with Customer Role | 5_M_Runbook_SEPA_M5 | 2023-10-27 | 13:00 | 2023-10-27 | 17:00 | 100% | 2023-10-27 | f | S. Dovalin | A. Green
TR | M5 |  | Acceptance of SEPA Mandate |  |  | 2023-10-30 | 8:00 | 2023-10-30 | 14:00 | 100% | 2023-10-30 | f |  |  | J. Barela
PM | M5 |  | Direct Transfer of Customer Material Info Records | Business Partners, Materials | 43_M_Runbook_CUS_M_INFO_M5 | 2023-10-27 | 8:00 | 2023-10-27 | 14:00 | 100% | 2023-10-27 | f | W. Axmaker | R. Yang
PM | M5 |  | Acceptance of Customer Material Info Records |  |  | 2023-10-30 | 8:00 | 2023-10-30 | 15:00 | 100% | 2023-10-30 | f |  |  | H. Packard
| M5 | X | Week 2 |  |  | 2023-10-30 | 8:00 | 2023-11-03 | 17:00
FI | M5 |  | Migration of Main Assets and Transactional Data | GL Accounts, Internal Orders, Cost Centers, Business Partners | 3_M_Runbook_AST_M5 4_M_Runbook_AST_TR_M5 | 2023-10-30 | 8:00 | 2023-10-31 | 17:00 | 100% | 2023-10-31 | f | S. Tigner | A. Castree
FI | M5 |  | Migration of Sub-Assets and Transactional Data | Assets, GL Accounts, Internal Orders, Cost Centers, Business Partners | 3_M_Runbook_AST_M5 4_M_Runbook_AST_TR_M5 | 2023-11-01 | 8:00 | 2023-11-01 | 17:00 | 100% | 2023-11-01 | f | S. Tigner | A. Castree
FI | M5 |  | Acceptance of Assets and Transactional Data |  |  | 2023-11-02 | 8:00 | 2023-11-03 | 17:00 | 100% | 2023-11-03 | f |  |  | A. Lolmaugh
FI | M5 |  | Migration of AR Open Items | Business Partner, GL Accounts, CO Objects, FI Characteristics | 23_M_Runbook_AR_OI_M5 | 2023-10-30 | 8:00 | 2023-11-01 | 12:00 | 100% | 2023-11-01 | f | A. Castree | S. Dovalin
FI | M5 |  | Acceptance of AR Open Items |  |  | 2023-11-01 | 12:00 | 2023-11-03 | 12:00 | 100% | 2023-11-03 | f |  |  | J. Barela
FI | M5 |  | Migration of AP Open Items | Business Partner, GL Accounts, CO Objects, FI Characteristics | 24_M_Runbook_AP_OI_M5 | 2023-10-30 | 8:00 | 2023-11-01 | 12:00 | 100% | 2023-11-01 | f | S. Dovalin | A. Castree
FI | M5 |  | Acceptance of AP Open Items |  |  | 2023-11-01 | 12:00 | 2023-11-03 | 12:00 | 100% | 2023-11-03 | f |  |  | W. Desegur
FI | M5 |  | Migration of GL Open Items | GL Accounts, CO Objects, FI Characteristics | 25_M_Runbook_GL_OI_M5 | 2023-10-30 | 8:00 | 2023-11-01 | 12:00 | 100% | 2023-11-01 | f | S. Tigner | A. Green
FI | M5 |  | Acceptance of GL Open Items |  |  | 2023-11-01 | 12:00 | 2023-11-03 | 12:00 | 100% | 2023-11-03 | f |  |  | W. Desegur
FI | M5 |  | Migration of GL Open Items (Ledger Group Spec.) | GL Accounts, CO objects, FI Characteristics | 25_M_Runbook_GL_OI_M5 | 2023-11-01 | 13:00 | 2023-11-02 | 17:00 | 100% | 2023-11-02 | f | S. Tigner | A. Green
FI | M5 |  | Acceptance of All GL Open Items (Ledger Group Spec.) |  |  | 2023-11-03 | 8:00 | 2023-11-03 | 13:00 | 100% | 2023-11-03 | f |  |  | J. Thomson
FI | M5 |  | Migration of GL Balances | GL Accounts, FI Characteristics | 26_M_Runbook_GL_BLC_M5 | 2023-11-02 | 8:00 | 2023-11-03 | 17:00 | 100% | 2023-11-03 | f | S. Tigner | A. Green
FI | M5 |  | Acceptance of GL Balances |  |  | 2023-11-06 | 8:00 | 2023-11-07 | 17:00 | 100% | 2023-11-07 | f |  |  | J. Thomson
PM | M5 |  | Migration of Functional Locations | Work Center, PSP-Elements, Settlement Rules, Business Partners, Assets, Cost Centers | 16_M_Runbook_FUN_LOC_M5 | 2023-11-02 | 8:00 | 2023-11-02 | 17:00 | 100% | 2023-11-02 | f | I. Clendenning | S. A. Foster
PM | M5 |  | Acceptance of Functional Locations |  |  | 2023-11-03 | 8:00 | 2023-11-03 | 15:00 | 100% | 2023-11-03 | f |  |  | J. McCoffin
TR | M5 |  | Transfer of Facilities | Business Partners | 35_M_Runbook_FAC_M5 | 2023-10-30 | 8:00 | 2023-10-30 | 9:00 | 100% | 2023-10-30 | f | V. Shiplet | P. J. White
TR | M5 |  | Acceptance of Facilities |  |  | 2023-10-30 | 9:00 | 2023-10-30 | 12:00 | 100% | 2023-10-30 | f |  |  | S. Oglebay
PM | M5 |  | Direct Transfer of Equipments | CO Objects, Business Partners, Assets, Functional Locations | 15_M_Runbook_EQP_M5 | 2023-11-03 | 8:00 | 2023-11-03 | 17:00 | 100% | 2023-11-03 | f | I. Clendenning | S. A. Foster
PM | M5 |  | Acceptance of Equipments |  |  | 2023-11-06 | 8:00 | 2023-11-06 | 17:00 | 100% | 2023-11-06 | f |  |  | J. McCoffin
FI | M5 |  | Transfer of Recurring Entries | Business Partners, GL Accounts, CO Objects, FI Characteristics | 27_M_Runbook_RE_M5 | 2023-10-31 | 8:00 | 31/10/023 | 14:00 | 100% | 2023-10-31 | f | V. Long | B. Sheftall
FI | M5 |  | Acceptance of Recurring Entries |  |  | 2023-11-01 | 8:00 | 2023-11-02 | 15:00 | 100% | 2023-11-02 | f |  |  | W. Desegur
TR | M5 |  | Transfer of Bank Guarantees | Business Partners, Facilities | 34_M_RUNBOOK_BANK_GRT_M5 | 2023-10-30 | 9:00 | 2023-10-30 | 17:00 | 100% | 2023-10-30 | f | V. Shiplet | P. J. White
TR | M5 |  | Acceptance of Bank Guarantees |  |  | 2023-10-31 | 8:00 | 2023-10-31 | 15:00 | 100% | 2023-10-31 | f |  |  | S. Oglebay
TR | M5 |  | Migration of IR Instruments | Business Partners | 36_M_Runbook_IR_M5 | 2023-10-31 | 8:00 | 2023-10-31 | 17:00 | 100% | 2023-10-31 | f | V. Shiplet | P. J. White
TR | M5 |  | Acceptance of IR Instruments |  |  | 2023-11-01 | 8:00 | 2023-11-01 | 15:00 | 100% | 2023-11-01 | f |  |  | S. Oglebay
FI | M5 |  | Transfer of Dispute Cases | Business Partners, AR Open Items, SAP Users | 28_M_Runbook_DCASE_M5 | 2023-11-03 | 8:00 | 2023-11-03 | 17:00 | 100% | 2023-11-03 | f | V. Long | B. Sheftall
FI | M5 |  | Acceptance of Dispute Cases |  |  | 2023-11-06 | 8:00 | 2023-11-06 | 17:00 | 100% | 2023-11-06 | f |  |  | J. Barela
| M5 | X | Week 3 |  |  | 2023-11-06 | 8:00 | 2023-11-10 | 17:00
Calim | M3 |  | Migratioon of Claim Office | GL Accounts, FI Postings, Business Partners, Equipments, Functional Locations | n/a | 2023-11-06 | 8:00 | 2023-11-07 | 17:00 | 100% | 2023-04-26 | f | A. J Miller | A. J Miller | A. J Miller
CO | M5 |  | Migration of PL Balances | GL Accounts, Cost Centers, FI Characteristics | 41_M_Runbook_PL_BLC_M5 | 2023-11-06 | 8:00 | 2023-11-06 | 12:00 | 100% | 2023-11-06 | f | V. Long | A. Castree
CO | M5 |  | Acceptance of PL Balances |  |  | 2023-11-06 | 12:00 | 2023-11-06 | 17:00 | 100% | 2023-11-06 | f |  |  | S. Luis
PM | M5 |  | Direct Transfer of Measuring Points | Equipments, Functional Locations | 31_M_Runbook_MEASP_M5 | 2023-11-06 | 8:00 | 2023-11-06 | 12:00 | 100% | 2023-11-06 | f | I. Clendenning | J. Hullet
PM | M5 |  | Acceptance of Measuring Points |  |  | 2023-11-06 | 13:00 | 2023-11-07 | 15:00 | 100% | 2023-11-07 | f |  |  | E. Ulibari
PM | M5 |  | Migration of Maintenance Plans | Equipments, Functional Locations, Work Centers, Materials, Task Lists | 37_M_Runbook_PMP_M5 | 2023-11-06 | 8:00 | 2023-11-06 | 17:00 | 100% | 2023-11-06 | f | I. Clendenning | J. Hullet
PM | M5 |  | Acceptance of Maintenance Plans |  |  | 2023-11-07 | 8:00 | 2023-11-07 | 17:00 | 100% | 2023-11-07 | f |  |  | J. McCoffin
PM | M5 |  | Direct Transfer of Notifications | Equipments, Functional Locations, Work Centers, Measuring Points | 32_M_Runbook_NOT_M5 | 2023-11-07 | 8:00 | 2023-11-07 | 17:00 | 100% | 2023-11-07 | f | I. Clendenning | J. Hullet
PM | M5 |  | Acceptance of Notifications |  |  | 2023-11-08 | 8:00 | 2023-11-08 | 17:00 | 100% | 2023-11-08 | f |  |  | E. Ulibari
PM | M5 |  | Direct Transfer of Plant Maintenance Open Orders | CO Objects, FI Characteristics, Activity Types, Equipments, Functional Location, Materials, Work Centers, Work Schedules, Service Schedules, Notifications | 30_M_Runbook_PM_ORD_M5 | 2023-11-08 | 8:00 | 2023-11-08 | 17:00 | 100% | 2023-11-08 | f | I. Clendenning | S. A. Foster
PM | M5 |  | Acceptance of Plant Maintenance Open Orders |  |  | 2023-11-09 | 8:00 | 2023-11-09 | 12:00 | 100% | 2023-11-09 | f |  |  | K. Monroe
PM | M5 |  | Direct Transfer of Measurenment Documents | Equipments, Functional Locations, Mesuring Points, Notifications | 33_M_Runbook_MEAS_DOC_M5 | 2023-11-09 | 8:00 | 2023-11-09 | 12:00 | 100% | 2023-11-08 | f | I. Clendenning | J. Hullet
PM | M5 |  | Acceptance of Measurenment Documents |  |  | 2023-11-09 | 13:00 | 2023-11-09 | 17:00 | 100% | 2023-11-10 | f |  |  | E. Ulibari
PM | M5 |  | Direct Transfer of Object Classification | Materials, Equipments, Functional Locations, Notifications, Classes, Characteristics | 44_M_Runbook_OBJ_CLASS_M5 | 2023-11-09 | 8:00 | 2023-11-09 | 17:00 | 100% | 2023-11-08 | f | B. Sheftall | S. A. Foster
PM | M5 |  | Acceptance of Object Classification |  |  | 2023-11-10 | 8:00 | 2023-11-10 | 12:00 | 100% | 2023-11-09 | f |  |  | K. Monroe
PR | M5 |  | Upload of Open Purchase Orders | Business Partners, CO Objects, PM Orders, MM Master Data, FI Characteristics, GL Accounts, AP Open Items | 37_M_Runbook_OPO_M5 | 2023-11-08 | 13:00 | 2023-11-09 | 12:00 | 100% | 2023-11-09 | f | W. Axmaker | K. Seabrook
PR | M5 |  | Acceptance of Open Purchase Orders |  |  | 2023-11-09 | 12:00 | 2023-11-10 | 17:00 | 100% | 2023-11-10 | f |  |  | W. Uharriet
Note on Q10: Tap "Today" to go to the current day on the calendar
Note on Q12: Set the start date for the data migration process

## Definition of Color
Definition of Color
[1] Time Bar
[2] Day Bar
[3] Milestome
A= | 1 | B= | 1 | C= | 2 | D= | 1
Green bright
Blue Bright
Red bright
Blue gray bright
Green
Blue gray
Red
Blue gray dark
Choose the color:
A = Plan
B = Finished
Yellow
Orange
Blue
Gray
Choose the color:
Blue dark
Red dark
Green dark
Gray dark
Choose the color:
D = Meilenstein
C = Tagesbalken